COMSATS University Islamabad, 
Abbottabad Campus

Project Proposal 
(SCOPE DOCUMENT)

for

<Saving Bot>
Version 1.0

By

BASIT IQBAL      CIIT/FA21-BSE-050/ATD

FATIMA AFTAB      CIIT/FA21-BSE-080/ATD

WALEED RASHID      CIIT/FA21-BSE-162/ATD

Supervisor
Syed Shahab Zarin

Bachelor of Science in Computer Science (2021-2024)

SCOPE DOCUMENT REVSION HISTORY

| No. | Comment | Action |
| --- | --- | --- |

Supervisor Signature

Date:

Table of Contents

1.	INTRODUCTION	9

2.	PROBLEM STATEMENT	10

3.	PROBLEM SOLUTION FOR PROPOSED SYSTEM	10

3.1.	Object Detection	10

3.2.	Web Scrapping for Price Information	10

3.3.	Seamless User Interface	10

4.	RELATED SYSTEM ANALYSIS/LITERATURE REVIEW	11

4.1.	Existing Similar Systems	11

4.1.1.	General Price Comparison Websites:	11

4.1.2.	Browser Extensions:	11

4.1.3.	Barcode Scanners:	11

4.2.	Existing Similar Systems in Tabular Form	12

5.	ADVANTAGES AND BENEFITS OF PROPOSED SYSTEM	13

5.1.	Enhanced User Convenience	13

5.2.	Accurate Item Identification	13

5.3.	Real-time Price Comparison	13

5.4.	Comprehensive and Up-to-date Data	13

5.5.	Cost Savings	13

5.6.	Seamless User Interface	13

5.7.	Personalized Shopping Experience	13

5.8.	Wide Range of Retailers	14

5.9.	Increased Efficiency	14

5.10.	Enhanced Decision -Making	14

6.	SCOPE	15

6.1.	Functionality	15

6.1.1.	Item Identification	15

6.1.2.	Price Comparison	15

6.1.3.	Additional Features (Optional for future development)	15

6.2.	Technical Considerations	15

6.2.1.	Image Recognition Model	15

6.2.2.	Data Scrapping	15

6.3.	Exclusions	15

6.4.	Platform	16

6.5.	Future Development	16

7.	SYSTEM LIMITATIONS/CONSTRAINTS	17

7.1.	Limitations	17

7.1.1.	Image Recognition Accuracy	17

7.1.2.	Data Scrapping Challenge	17

7.1.3.	Limited Scope (Initial Version)	17

7.2.	Constraints	17

7.2.1.	Computational Resources	17

7.2.2.	Real-Time Price Updates	17

7.2.3.	Ethical Consideration	17

8.	SOFTWARE PROCESS METHODOLOGY	18

8.1.	Flexibility	18

8.2.	Reduced Risk	18

8.3.	Prioritization	18

8.4.	Better Quality Control	18

8.5.	Adaptability to Change	18

9.	TOOLS AND TECHNOLOGIES	19

10.	PROJECT STAKEHOLDERS AND ROLES	19

11.	DATA GATHERING APPROACH	20

11.1.	Using Kaggle data set	20

11.2.	Doing web scraping	20

12.	CONCEPTS	20

13.	GANTT CHART	21

13.1.	Gantt Chart using MS Project	21

13.2.	Gantt Chart using MS Excel	22

14.	NETWORK DIAGRAM	23

14.1.	Activities Details	23

14.2.	Activity on Node	23

14.2.1.	Notations	23

14.2.2.	Diagram	23

14.3.	Activity on Arrow	24

15.	WORK BREAKDOWN STRUCTURE (WBS)	25

16.	COST ESTIMATION OF PROJECT	26

16.1.	Basic Model	26

16.1.1.	Effort:	26

16.1.2.	Development Time	26

16.1.3.	Staff Size	27

16.1.4.	Productivity	27

16.2.	Intermediate Model	28

16.2.1.	EAF according to Project	29

16.2.2.	Effort Adjustment Factor	30

16.2.3.	Effort:	30

16.2.4.	Development Time	30

16.2.5.	Staff Size	30

16.2.6.	Productivity	30

16.3.	Detailed Model	31

16.3.1.	Major Phases	31

16.3.2.	Distribution of Effort	31

16.3.3.	Effort for each Phase	31

16.3.4.	Development Time for each Phase	32

17.1.	Risk Identification	33

17.2.	Risk Analysis using SWOT	34

17.2.1.	Strength	34

17.2.2.	Weakness	34

17.2.3.	Opportunity	34

17.2.4.	Threats	34

18.	QUALITY STANDARDS FOR SAVINGBOT	36

18.1.	Functionality	36

-	Accuracy:	36

-	Completeness:	36

18.2.	Reliability	36

-	Availability:	36

-	Fault Tolerance:	36

18.3.	Usability	36

-	User Interface (UI):	36

-	User Experience (UX):	36

18.4.	Performance Efficiency	36

-	Response Time:	36

-	Resource Utilization:	36

18.5.	Security	36

-	Data Protection:	36

18.6.	Maintainability	36

-	Modularity:	36

-	Scalability:	36

18.7.	Portability	36

-	Cross-Platform Compatibility:	36

-	Adaptability:	36

19.	REFERENCES	38

20.	PLAGIARISM REPORT	38

Figure 1:Gantt Chart using MS Project	22

Figure 2:Gantt Chart using MS Excel	23

Figure 3:Notation	24

Figure 4:Activity on Node Detailed	24

Figure 5:Activity on Arrow	25

Figure 6:Work Breakdown Structure of System	26

Figure 7:Constant Values According to type of Project.	27

Figure 8:Factors of Intermediate Model	29

Table 1:Related System Analysis with proposed project solution	12

Table 2:Tools and Technologies for Proposed System	19

Table 3:Project Stakeholders and their Roles	19

Table 4:Activities Details	23

Table 5:Project EAF	29

Table 6:Project’s Risks	34

Table 7:SWOT Analysis	35

Project Category: (Select all the major domains of proposed project)

- A-Mobile Application/Information System B-Web Application/Mobile Application                                                 C- Problem Solving and Artificial Intelligence   D-Simulation and Modelling   E- Smartphone Application  F- Smartphone Game     G- Networks  H- Image ProcessingOther (specify category) ______________________

ABSTRACT

The endeavor at hand is the development of an AI-powered Shopping Optimizing APP, (i.e. Saving Bot) designed to revolutionize the shopping experience. Targeting the individuals seeking the best deals prices on fashion items. This application will use advanced image recognition algorithms to identify the items uploaded by users.  The algorithm that we will use is VGG-16 which is an image recognition model that is used to identify the objects. Hence this algorithm will swiftly identify the attributes of items like color, patterns, and style facilitating precise searches across multiple online stores.

Upon user submission, the application systematically searches various online platforms extracting information from variety of retailers. Using its skills in computer programming and data analysis, the app collects a lot of price options. Users then see a list of stores with prices and links to buy things easily.

The project combines advanced AI-Technology with user-friendly interface to streamline shopping experience for our target users. By giving users instant access to the best deals, the app changes how easy and valuable shopping experience can be.

# INTRODUCTION

In the current digital era, technology continues to transform the way we interact with the world, including how we shop. One of the most important advancements in this domain is the integration of artificial intelligence (AI) and machine learning (ML) into everyday applications. AI technologies, particularly in the fields of image recognition and data analysis, are revolutionizing various industries by enabling more intelligent and efficient processes.

Image recognition is a branch of AI (artificial intelligence) that encompasses the training algorithms to identify and classify objects within images. These algorithms, such as the widely used VGG-16 model, can analyses visual data to detect specific features like color, shape, and patterns. This technology has many applications, from facial recognition systems to automated quality control in manufacturing and industry.

Another crucial and vital technology is web scraping, a technique used to extract data from websites. By automating the process of gathering information, web scraping allows for the efficient and convenient collection of large datasets from multiple sources. This data can then be analyzed and used to provide valuable insights, such as comparing prices across different online retailers, which can also be used to make predictions.

Combining these advanced technologies creates powerful tools that can significantly enhance user experiences in various domains, including online shopping. Online shopping has become a staple of modern life, offering convenience and a vast array of choices. However, finding the best deals can be time-consuming and frustrating due to the overwhelming number of options and the difficulty in comparing prices across different websites.

To address these challenges, we propose the development of the Saving Bot, an AI-powered shopping optimization app designed to streamline the online shopping experience. The Saving Bot leverages the capabilities of image recognition and web scraping to offer a unique and efficient solution for finding the best deals on fashion items.

Users can simply upload a picture of the clothing item they are interested in, and the app's sophisticated image recognition algorithm, based on the VGG-16 model, accurately identifies the item's attributes. The app then utilizes advanced web scraping techniques to gather real-time pricing information from numerous online retailers. By compiling and comparing these prices, the Saving Bot presents users with a comprehensive list of options, ensuring they can easily find the best deals available.

This project not only aims to make online shopping more accessible and affordable but also promises to enhance user satisfaction by providing a seamless and intuitive interface. By integrating cutting-edge AI technology with practical application, the Saving Bot stands to revolutionize the way users shop for fashion items online, offering a smarter and more efficient alternative to traditional methods.

# PROBLEM STATEMENT

Online Shopping is a Hellish experience! When you find the perfect outfit, but only in size they haven’t invented it yet. Shoppers are frustrated with the unlimited number of stores, the hassle of finding the best price, and have difficulty comparing prices and outfits and sizes across different products. Now in this continuously evolving world what we need is a user-friendly app that uses curing edge technology to automate this process and do the work of comparison for us.

# PROBLEM SOLUTION FOR PROPOSED SYSTEM

The Saving Bot tackles the challenges of online shopping with a multi-functional approach, featuring these key elements:

## Object Detection

The app uses VGG-16 for the detection of clothes from the images uploaded by the user to accurately identify the style, color, and pattern of the clothes, enabling precise searches and comparisons.

## Web Scrapping for Price Information

Advanced web scraping techniques are used to gather real time pricing information from numerous online retailers, ensuring that the user will have access to the most up-to-date data.

## Seamless User Interface

A user-friendly interface is designed to provide an intuitive and hassle-free shopping experience, allowing users to navigate the app effortlessly and make informed choices.

# RELATED SYSTEM ANALYSIS/LITERATURE REVIEW

## Existing Similar Systems

### General Price Comparison Websites:

Websites like Google shopping and Shopzilla allow users to search for a specific item and compare prices across various online stores. However, these websites require users to know the item's name or brand beforehand. They lack the image recognition capability of your proposed application.

### Browser Extensions:

Browser extensions like Honey or Invisible Hand automatically search for coupons and price comparisons while users shop online. However, they are limited to the store the user is currently browsing and cannot search for an item across multiple stores based on an image.

### Barcode Scanners:

Mobile apps like Shop Savvy or Amazon app allow users to scan barcodes of physical products to find online prices. They require the product to have a barcode and cannot identify items based solely on an image.

## Existing Similar Systems in Tabular Form

| S.NO | Similar Systems | Similar Functionality | Limitation | Proposed Project Solution |
| --- | --- | --- | --- | --- |
| 1 | Google shopping | General Price Comparison Websites | Can’t do image recognition. | Uses image recognition to identify items from an image uploaded. |
| 2 | Honey | Browser Extensions | Limited to Current Online Store. | Searches for Price Comparison on various stores based on image uploaded. |
| 3 | Shop Savvy | Barcode Scanners | Require physical products with barcode. | Identify item from an image eliminating the need for a barcode. |
| 4 | Invisible Hand | Browser Extensions | Limited to Current Online Store. | Searches for Price Comparison on various stores based on image uploaded. |
| 5 | Shopzilla | General Price Comparison Websites | Can’t do image recognition. | Uses image recognition to identify items from an image uploaded. |
| 6 | Amazon | Barcode Scanners | Require physical products with barcode. | Identify item from an image eliminating the need for a barcode. |

Table 1:Related System Analysis with proposed project solution

# ADVANTAGES AND BENEFITS OF PROPOSED SYSTEM

## Enhanced User Convenience

Users can easily upload pictures of desired fashion items, eliminating the need to manually search through numerous websites. This streamlines the shopping process, saving valuable time and effort.

## Accurate Item Identification

The sophisticated image recognition algorithm, based on the VGG-16 model, ensures precise identification of clothing items. This accuracy helps in providing relevant search results and enhances the overall user experience.

## Real-time Price Comparison

By leveraging advanced web scraping techniques, the Saving Bot gathers real-time pricing information from multiple online retailers. This allows users to compare prices quickly and efficiently, ensuring they find the best deals available.

## Comprehensive and Up-to-date Data

The system continuously updates its database with the latest prices and product availability, providing users with the most current information. This helps in making informed purchasing decisions.

## Cost Savings

The primary goal of the Saving Bot is to help users find the best deals on fashion items. By comparing prices across different retailers, users can identify significant cost savings, making their shopping experience more affordable.

## Seamless User Interface

The app is designed with a user-friendly and intuitive interface, making it accessible to a wide range of users, regardless of their technical expertise. This ease of use enhances overall user satisfaction.

## Personalized Shopping Experience

The AI algorithms can learn from user preferences and past behaviours, offering personalized recommendations and improving the relevance of search results over time. This personalization makes the shopping experience more tailored to individual needs.

## Wide Range of Retailers

The web scraping capabilities allow the Saving Bot to gather data from a vast array of online retailers, ensuring a comprehensive selection of options. This variety helps users find not only the best prices but also the best products.

## Increased Efficiency

Automating the process of price comparison and product identification significantly reduces the time and effort required for online shopping. Users can focus on other tasks while the Saving Bot does the heavy lifting.

## Enhanced Decision -Making

With access to detailed information and price comparisons, users can make more informed purchasing decisions. This transparency helps in avoiding buyer’s remorse and ensures satisfaction with the purchased items.

# SCOPE

## Functionality

### Item Identification

- Scope: The application will focus on identifying clothing and fashion items in user-uploaded images.

- Accuracy: The application will strive for high accuracy, aiming to identify similar items with slight variations in color or pattern.

### Price Comparison

  - Scope: The application will focus on identifying clothing and fashion items in user-uploaded images.

  - Accuracy: The application will strive for high accuracy, aiming to identify similar items with slight variations in color or pattern.

### Additional Features (Optional for future development)

  - Users can filter search results by brand, size, or color.

  - The application can suggest similar items based on the uploaded image and user preferences.

  - Integration with user reviews from trusted sources can be considered.

## Technical Considerations

### Image Recognition Model

The application will leverage a pre-trained image recognition model like VGG-16, fine-tuned on a relevant fashion image dataset (e.g., Kaggle Fashion Dataset).

### Data Scrapping

  - The application will ethically scrape price data from online stores, respecting their terms of service.

  - The system will be designed to handle data from multiple stores efficiently.

## Exclusions

- The application will not include features like barcode scanning or in-app purchasing capabilities (users will be directed to retailer websites for purchases).

- Initially, the application will focus on English language support.

## Platform

The application will be developed as a cross-platform mobile app (iOS and Android) for wider user accessibility.

## Future Development

Based on user feedback and market demands, the scope can be expanded to include additional product categories, a wider range of stores, and more advanced features.

# SYSTEM LIMITATIONS/CONSTRAINTS

## Limitations

### Image Recognition Accuracy

VGG-16, while powerful, might not perfectly capture subtle variations in clothing items (like slight differences in fabric texture or embellishments). This could lead to inaccurate price comparisons for similar but not identical items.

### Data Scrapping Challenge

Websites may change their layout or data structure frequently, requiring the app to adapt its scraping techniques to maintain functionality.

Retailers might implement anti-scraping measures, making it difficult for the app to access price data reliably.

### Limited Scope (Initial Version)

Focusing on clothing initially limits the app's usability for other product categories.

Including only a few stores restricts users' access to the broadest range of deals.

## Constraints

### Computational Resources

Running image recognition models and scraping data requires processing power. This may limit the app's scalability to a large user base or restrict the number of stores it can search simultaneously.

### Real-Time Price Updates

Constantly checking prices across multiple stores can be resource intensive. Striking a balance between update frequency and efficient data usage is crucial.

### Ethical Consideration

Data scraping must comply with website terms of service and avoid overloading their servers.

# SOFTWARE PROCESS METHODOLOGY

Agile development is ideal for the Saving Bot Mobile Application for several reasons:

  - Flexibility

As user needs or senior technology adoption evolves, agile development allows for incorporating new features or functionalities efficiently.

  - Reduced Risk

By delivering features in small increments, agile development minimizes the risk of investing heavily in features that seniors may not find useful.

  - Prioritization

Agile prioritizes the most impactful features first, ensuring the core functionalities that enhance well-being are delivered quickly.

## Better Quality Control

Regular testing and continuous feedback in Agile development ensure a high-quality, reliable application.

## Adaptability to Change

Agile's focus on responsiveness allows the application to quickly adapt to new requirements, user feedback, and technological advancements.

# TOOLS AND TECHNOLOGIES

We will be using the following tools and technologies for building this project.

| Tools And Technologies | Tools | Version | Rationale |
| --- | --- | --- | --- |
|  | MS Visual Studio | 1.82 | IDE |
|  | Mongo DB | 2015 | DBMS |
|  | MS Project | CSC 6 | Management |
|  | MS Word | 2015 | Documentation |
|  | MS Power Point | 2015 | Presentation |
|  | Star UML | 2.0.5 | Mock-ups Creation |
|  | Technology | Version | Rationale |
|  | React Native | 0.72 | Framework |
|  | Express JS | 4.19.1 | Framework |
|  | Node JS | 21.0.0 | Run time environment |
|  | Java Script | ES 13 | Scripting Language |

Table 2:Tools and Technologies for Proposed System

# PROJECT STAKEHOLDERS AND ROLES

Write down the project stakeholders and their roles.

| Project Sponsor | COMSATS University, Islamabad Committee |
| --- | --- |
| Stakeholder | Mention your stakeholders with their roles and responsibilities. Default option will be: - Group Members: BASIT IQBAL, Fatima Aftab, Waleed Rashid - Project Supervisor Name: Mr. Syed Shahab Zarin - Final Year Project Committee: Evaluation of project |

Table 3:Project Stakeholders and their Roles

# DATA GATHERING APPROACH

The data gathering approach for this project will include:

## Using Kaggle data set

Leveraging pre-existing, high-quality datasets from Kaggle to obtain relevant information efficiently.

## Doing web scraping

Extracting real-time data from websites to ensure the application has up-to-date and comprehensive information.

# CONCEPTS

Concepts to be learned during this project include:

- Object Detection techniques.

- Using Kaggle Data set to Train Model (AI).

- Web Scrapping

- User Authentication and Authorization

- Database design and management

- Responsive Mobile App design

# GANTT CHART

## Gantt Chart using MS Project

Figure 1:Gantt Chart using MS Project

## Gantt Chart using MS Excel

Figure 2:Gantt Chart using MS Excel

# NETWORK DIAGRAM

## Activities Details

| Activity Name | Duration | Predecessor |
| --- | --- | --- |
| Project Initiation | 11 | - |
| Project Plan | 17 | Project Initiation |
| Project Design | 15 | Project Plan |
| Development | 79 | Project Design |
| Testing | 15 | Development |
| Deployed | 10 | Testing |
| Delivered | 7 | Delivered |

Table 4:Activities Details

## Activity on Node

### Notations

Figure 3:Notation

### Diagram

Figure 4:Activity on Node Detailed

## Activity on Arrow

Figure 5:Activity on Arrow

# WORK BREAKDOWN STRUCTURE (WBS)

Figure 6:Work Breakdown Structure of System

# COST ESTIMATION OF PROJECT

Total Line of Code:

Total line of Code = 200KLOC

Type of Project:

As there are 200KLOC so it falls under the category of “semidetached”.

## Basic Model

According to the type of project we will pick the value of a, b, c, d from the following table.

Figure 7:Constant Values According to type of Project.

According to the table a=3.0, b=1.12, c=2.5, d=0.35.

Now we start the calculation.

### Effort:

E=ab(KLOC)bb

E= 3.0 (200)1.12

E= 3.0×545.01

E= 1133.12 Person-Months

### Development Time

D=cb(Effort)db

D= 2.5 (1133.120.35)

D=2.5×11.72

D=29.30 Months

### Staff Size

SS= EffortDevelopment Time

SS= 1133.12 29.30

SS= 38.67 People

### Productivity

P=KLOCEffort

P= 2001133.12

P= 0.1765 KLOC/PM

## Intermediate Model

Now we will find the factors form the following table:

Figure 8:Factors of Intermediate Model

### EAF according to Project

| S. No | Attribute | Level | Reason of selecting level | Value from table |
| --- | --- | --- | --- | --- |
| 1 | Required software reliability extent | High | Financial data (price comparisons) is involved, so minimal errors and crashes are crucial. | 1.15 |
| 2 | Size of the application database | Low | As it would store only the user info and some basic info related to the items | 0.94 |
| 3 | The complexity of the product | High | As first it would detect the item and then it will web scrape the items related to its which are available then it will compare the prices and at last it will show the items. | 1.15 |
| 4 | Run-time performance constraints | Very High | As the bot is using third part VGG-16 model to detect the item so it might take some time then it must scrape the websites for better results so it will take time | 1.30 |
| 5 | Memory constraints | Low | As the app wouldn’t store that much info | 1.00 |
| 6 | Required turnabout time | Normal | Instant responses aren't crucial. Users likely expect a few seconds for search results. | 1.00 |
| 7 | Analyst capability | Normal | As the analyst will have to understand the fashion trends, which keep on changing | 1.00 |
| 8 | Programming language experience | Normal | As we would be using VGG-16 which is per-built but we need a good experience in coding to do web-scraping and for front and backend development. | 1.00 |

Table 5:Project EAF

### Effort Adjustment Factor

EAF = ∏ (factors)

EAF = 1.62

### Effort:

E=ab(KLOC)bb*EAF

E= 3.0 (200)1.12 * 1.62

E= 3.0×545.01 × 1.62

E= 1835.12 Person-Months

### Development Time

D=cb(Effort)db

D= 2.5 (1835.120.35)

D=2.5×11.72

D= 29.30 Months

D=29.30 Months

### Staff Size

SS= EffortDevelopment Time

SS = 1835.1229.30

SS= 62.63 Persons

### Productivity

P=KLOCEffort

P= 2001835.12

P= 0.109 KLOC/Person Months

## Detailed Model

To provide a detailed COCOMO estimation for the project with the identified major components, we'll allocate the total effort calculated earlier (1835.12 Person-Months) across these phases. Here’s how we can break it down:

### Major Phases

- Responsive Mobile App design

- Database design and management

- Web Scraping

- User Authentication and Authorization

- Object Detection by VGG-16

### Distribution of Effort

We'll assume a reasonable distribution of effort across these phases. This distribution will depend on the complexity and relative effort each component typically requires. A possible distribution could be as follows:

- Responsive Mobile App design: 25%

- Database design and management: 20%

- Web Scraping: 15%

- User Authentication and Authorization: 20%

- Object Detection by VGG-16: 20%

### Effort for each Phase

#### Responsive Mobile App design:

E= 1835.12×0.25

E=458.78Person-Months

#### Database design and management:

E=1835.12×0.20

E=367.02 Person-Months

#### Web Scraping:

E=1835.12×0.15

E=275.27 Person-Months

#### User Authentication and Authorization:

E=1835.12×0.20

E=367.02 Person-Months

#### Object Detection by VGG-16:

E=1835.12×0.20

E=367.02 Person-Months

### Development Time for each Phase

To calculate the development time for each component, we will use the formula:

D=cb(Effort)db

Where, 𝑐=2.5 and 𝑑=0.35

Let's calculate the development time for each component.

#### Responsive Mobile App design:

𝐷=2.5×(458.78)0.35

D=7.85 Months

#### Database design and management:

𝐷=2.5×(367.02)0.35

D=7.17 Months

#### Web Scraping:

𝐷=2.5×(275.27)0.35

D=6.26 Months

#### User Authentication and Authorization:

𝐷=2.5×(367.02)0.35

D=7.17 Months

#### Object Detection by VGG-16:

𝐷=2.5×(367.02)0.35

D=7.17 Months

- RISK MANAGEMENT

## Risk Identification

| Risk | Potential Indicators |
| --- | --- |
| Technology | - Compatibility issues with mobile platforms (iOS, Android) - Slow performance in image processing - Delays in image recognition accuracy improvement - Issues integrating web scraping tools - Security vulnerabilities in web scraping modules - Failure to maintain up-to-date technology stack |
| People | - High turnover rates among team members - Inadequate training for new technology - Low motivation among team members - Interpersonal conflicts - Insufficient expertise in AI and machine learning - Poor collaboration - Low team engagement |
| Organizational | - Conflict between project goals and academic requirements - Lack of support from faculty - Delays in decision making - Internal miscommunications - Limited resource allocation |
| Tools | - Difficulty in setting up and maintaining development environment - Lack of tool support - Resistance to using selected development tools - Frequent tool crashes - Complaints about efficiency - Incompatibility between chosen software tools - Lack of necessary features |
| Requirements | - Ambiguity in project requirements - Conflicting requirements from different stakeholders (professors, team members) - Frequent changes in project scope - Unclear requirements from stakeholders - Late requirement additions - Incomplete requirement specifications - High rate of requirement changes |
| Estimation | - Inaccurate project timelines – - Delays in meeting milestones – - Unexpected defects impacting deadlines – - Underestimation of project complexity – - Unrealistic deadlines imposed by semester schedule |

Table 6:Project’s Risks

## Risk Analysis using SWOT

### Strength

- Innovative Use of AI: Utilizes advanced AI for object detection, offering a distinct advantage over traditional comparison tools.

- Multi-Platform Availability: Cross-platform design ensures accessibility on both iOS and Android devices.

- High User Value: Addresses significant user pain points in online shopping, providing a highly valuable service.

### Weakness

- High Development Costs: Requires substantial investment for development and ongoing maintenance.

- User Privacy Concerns: Handling of user-uploaded images may raise significant privacy issues.

- Technical Limitations: Potential inaccuracies in image recognition, especially for items with subtle differences.

### Opportunity

- Market Demand: Increasing consumer demand for convenient and efficient online shopping solutions.

- Advancements in AI: Continuous improvements in AI can further enhance the app’s performance and features.

- Global Reach: Expanding to international markets can significantly boost the user base and revenue potential.

### Threats

- Regulatory Changes: Evolving data privacy laws could impact how data is collected and used.

- Dependency on Internet: Requires stable internet access, which may limit usability in areas with poor connectivity.

- Negative User Feedback: Initial bugs or inaccuracies could result in negative reviews, impacting user adoption.

| SWOT Category | Details |
| --- | --- |
| Strength | - Innovative Use of AI - Multi-Platform Availability - High User Value. |
| Weaknesses | - High Development Cost - User Privacy Concern - Technical Limitations |
| Opportunities | - Market Demand - AI & ML Advancement - Global Research |
| Threats | - Regulatory Changes - Dependency on Internet Connectivity - Negative User Feedback |

Table 7:SWOT Analysis

# QUALITY STANDARDS FOR SAVINGBOT

## Functionality

- Accuracy: Ensuring the image recognition algorithm accurately identifies clothing items and the web scraping accurately collects price data.

- Completeness: The system should cover all necessary functionalities, such as item identification, price comparison, and user interface efficiency.

## Reliability

- Availability: The app should always be available to users, with minimal downtime.

- Fault Tolerance: The system should handle errors gracefully and recover quickly from failures.

## Usability

- User Interface (UI): The interface should be intuitive and easy to navigate.

- User Experience (UX): The overall user experience should be smooth, with quick response times and helpful feedback.

## Performance Efficiency

- Response Time: The system should provide quick responses to user actions, such as image uploads and price comparisons.

- Resource Utilization: The system should efficiently use computational resources to perform image recognition and web scraping tasks.

## Security

- Data Protection: User data should be securely handled, ensuring privacy and compliance with relevant regulations.

- Secure Data Scraping: The web scraping component should respect the terms of service of the websites being scraped and avoid triggering anti-scraping measures.

## Maintainability

- Modularity: The system should be built in a modular fashion to facilitate easy updates and maintenance.

  - Scalability: The system should be designed to handle increased load and new features as the user base grows.

## Portability

- Cross-Platform Compatibility: The app should be available on multiple platforms (iOS and Android) without significant changes in the codebase.

- Adaptability: The system should be easily adaptable to include new features and support additional product categories in the future.

# REFERENCES

https://www.kaggle.com/datasets/zalando-research/fashionmnist

https://www.shopzilla.com/

https://www.google.com/shopping?hl=en

# PLAGIARISM REPORT

Attach the Plagiarism report of your project scope document from library staff of Turnitin tool:

Sir, please add here as we don’t have Turnitin instructor account.